## Read Me (Nidhi)
NIKHIL — AI PRODUCT ENGINEER ¦ SPRINT PLAN
Sprint Master: Nidhi • Start: 20 June 2026 • Pace: ~8 hrs/day × 6 days (Sun off) • 2-week sprints
HOW TO USE THIS TRACKER
1. 'Sprint Board' = the live to-do board (Jira-style). Every task is one row.
2. Update the STATUS column only — pick from dropdown: To Do / In Progress / Done / Blocked. Colour changes automatically.
3. 'Dashboard' auto-calculates % done per sprint + overall. Nothing to fill there — it reads the board live.
4. 'Sprint Plan' = the big-picture map: each sprint's theme + the demo/deliverable that must exist at sprint-end.
5. 'Phase 2 Backlog' = growth items for AFTER the job / better-company push. No dates — pulled in later.
THE ONE TRIGGER THAT MATTERS
🚩 Applications START when M1 (Invoice Intelligence) is demo-able — slick UI + an eval dashboard proving accuracy.
That lands at the start of Sprint 4 (~early Aug). M1 = the whole job-getting engine. M2/M3 are interview talking-points built WHILE applying.
PRIORITY LEGEND
P0 = Core / non-negotiable (must-do to be apply-ready)
P1 = High (makes the application strong)
P2 = Phase 2 / growth (after job, or in parallel)
STATUS COLOURS
| To Do | In Progress | Done | Blocked
NOTE ON PACE (important)
Dates are TARGETS Nikhil owns — not deadlines. Sprints flex. Depth & correctness always beat speed; if a topic needs more time, the plan bends, the topic never gets skimmed.
Biggest single rock: Python / FastAPI / Pydantic (~100–130 hrs, spread across Sprints 1–2).
Biggest ROI differentiator: the LLMOps / Eval bucket (golden dataset + LLM-as-Judge) — this is what pushes pay into the ₹20L+ band.

## Sprint Board
ID | Sprint | Stream / Epic | Task | Sub-topics | Priority | Est Hrs | Status | Date Done | Notes
1-01 | Sprint 1 | Foundations | Embeddings (finish) | vectors, cosine vs euclidean, ANN/HNSW, vendor dedup | P0 | 8 | To Do |  | In progress now
1-02 | Sprint 1 | Foundations | Inference & sampling | temperature, top-p, top-k, greedy decoding | P0 | 6 | To Do |  | temp=0 for invoice extraction
1-03 | Sprint 1 | Foundations | Context window | token budget, sliding window, summarization | P0 | 6 | To Do
1-04 | Sprint 1 | Foundations | Hallucinations | causes, detection, grounding | P0 | 6 | To Do
1-05 | Sprint 1 | Courses | Anthropic: API Fundamentals | messages format, models, params | P0 | 4 | To Do |  | Colab
1-06 | Sprint 1 | Courses | Anthropic: Prompt Engineering (9 ch) | few-shot, chain-of-thought, system prompts | P0 | 12 | To Do |  | Colab
1-07 | Sprint 1 | Python | Python basics (start) | syntax vs JS, types, f-strings, control flow | P0 | 16 | To Do |  | Biggest rock — spreads into S2
1-08 | Sprint 1 | Setup | FinOps repo + Supabase | scaffold, env, Postgres + pgvector setup | P0 | 6 | To Do
1-09 | Sprint 1 | Foundations | Recall + Bolo locks | blank-recall, spoken explain, capsule lock | P0 | 6 | To Do |  | Forge — interview defense
2-10 | Sprint 2 | Python | Python basics (finish) | modules, error handling, file/JSON | P0 | 12 | To Do
2-11 | Sprint 2 | Python | FastAPI | routes, async endpoints, request/response | P0 | 10 | To Do |  | AI backend = Python
2-12 | Sprint 2 | Python | Pydantic | force LLM -> strict typed output | P0 | 8 | To Do |  | Core tool for reliable extraction
2-13 | Sprint 2 | Courses | Anthropic: Tool Use | function-calling course | P0 | 6 | To Do |  | Colab
2-14 | Sprint 2 | LLM-API | Structured / JSON output + validation | schema-forcing, parse, validate | P0 | 6 | To Do
2-15 | Sprint 2 | LLM-API | Multimodal / vision input | scanned & image invoice -> text | P0 | 8 | To Do |  | Extraction core
2-16 | Sprint 2 | LLM-API | Prompt engineering (hands-on) | extraction prompts, edge cases | P0 | 6 | To Do
2-17 | Sprint 2 | Domain | Compliance: TDS/TCS/DTAA (start) | 194C/194J/194H, TCS 206C, DTAA treaties | P0 | 10 | To Do |  | Re-learn from zero
2-18 | Sprint 2 | Cross-cut | 'Where NOT to use AI' | deterministic TDS math in code | P0 | 4 | To Do |  | Senior signal — defend in interview
2-19 | Sprint 2 | Build | M1: Upload -> extraction (Postman) | FastAPI endpoint, JSON out, no UI yet | P0 | 14 | To Do |  | First working slice
3-20 | Sprint 3 | Domain | Compliance: TDS/TCS/DTAA (finish) | thresholds, individual vs company rate | P0 | 8 | To Do
3-21 | Sprint 3 | LLMOps | Golden dataset + metrics | 30 real invoices, precision / recall / F1 | P0 | 10 | To Do |  | Secret weapon
3-22 | Sprint 3 | LLMOps | LLM-as-Judge | auto-grade extraction vs ground truth | P0 | 8 | To Do
3-23 | Sprint 3 | Courses | Anthropic: Evaluations | eval design, metrics | P0 | 6 | To Do |  | Colab
3-24 | Sprint 3 | LLMOps | Observability | tokens / latency / cost / prompt-version | P0 | 6 | To Do |  | api_logs table
3-25 | Sprint 3 | LLM-API | Confidence / trust scoring | 0-100 + action thresholds | P0 | 4 | To Do
3-26 | Sprint 3 | LLMOps | Guardrails + error handling + caching | input/output validation, DEMO_MODE | P0 | 8 | To Do
3-27 | Sprint 3 | LLM-API | Multi-model verification | Claude + GPT, agree/disagree | P1 | 8 | To Do
3-28 | Sprint 3 | Build | M1: Eval Dashboard | accuracy %, tracing, version compare | P0 | 14 | To Do |  | THE hireable artifact
4-29 | Sprint 4 | LLM-API | Streaming (SSE) + structured streaming | word-by-word, field-by-field UI | P0 | 8 | To Do
4-30 | Sprint 4 | LLMOps | Human-in-loop / 'Teach the AI' RLHF | user corrections -> re-evaluate | P0 | 8 | To Do |  | Anchor principle
4-31 | Sprint 4 | Full-Stack | React UI + build M1 frontend | refresh React, wire to backend | P0 | 14 | To Do
4-32 | Sprint 4 | Full-Stack | Vercel deploy | env, prod config, live URL | P0 | 4 | To Do
4-33 | Sprint 4 | LLMOps | Explainability / reasoning flowchart | 'Show AI Details' 3-level toggle | P1 | 6 | To Do
4-34 | Sprint 4 | Career | Resume + positioning narrative | ex-FinOps -> AI Product framing | P0 | 8 | To Do
4-35 | Sprint 4 | Career | LinkedIn + Loom demo video | profile rewrite + M1 walkthrough | P0 | 8 | To Do
4-36 | Sprint 4 | Career | 🚩 APPLICATIONS BEGIN | fintech-AI + applied-AI roles | P0 | 6 | To Do |  | Trigger: M1 demo-able
4-37 | Sprint 4 | Career | Interview prep: concept Q&A (start) | drill bucket concepts cold | P0 | 6 | To Do
5-38 | Sprint 5 | RAG | Vector search | pgvector + FAISS | P0 | 10 | To Do
5-39 | Sprint 5 | RAG | Chunking | semantic / section-aware | P0 | 6 | To Do
5-40 | Sprint 5 | RAG | Retrieval | top-K + hybrid (BM25 + semantic) | P0 | 6 | To Do
5-41 | Sprint 5 | RAG | RAG evaluation | faithfulness / groundedness | P0 | 6 | To Do
5-42 | Sprint 5 | RAG | Re-ranking | cross-encoder | P1 | 6 | To Do
5-43 | Sprint 5 | Build | M2: Bank Reconciliation | fuzzy match, anomaly, AI-explained mismatch | P1 | 16 | To Do
5-44 | Sprint 5 | Full-Stack | Basic Docker | docker-compose: FastAPI + pgvector | P1 | 8 | To Do |  | Cheap credibility — not K8s/cloud
5-45 | Sprint 5 | Career | Mock interviews (start) | cold, adversarial | P0 | 8 | To Do
5-46 | Sprint 5 | Career | Applications (ongoing) | apply + track | P0 | 6 | To Do
6-47 | Sprint 6 | Agents | ReAct agent (hands-on) | observe->reason->act, multi-tool | P0 | 12 | To Do
6-48 | Sprint 6 | Agents | Agentic reflection | self-correction on low confidence | P1 | 6 | To Do
6-49 | Sprint 6 | LLM-API | Model routing + batch processing | complexity->cheapest model, Batch API | P1 | 8 | To Do
6-50 | Sprint 6 | LLMOps | Prompt versioning + A/B | Supabase prompt_versions, rollback | P1 | 6 | To Do
6-51 | Sprint 6 | LLMOps | PII masking + injection defense | Aadhaar/bank mask, malicious input | P1 | 6 | To Do
6-52 | Sprint 6 | LLMOps | CI/CD with AI | eval as deploy-gate (Jest/Actions) | P1 | 6 | To Do
6-53 | Sprint 6 | Foundations | Light: NN / training-RLHF / jagged | interview-confidence depth only | P1 | 8 | To Do
6-54 | Sprint 6 | Career | Mock interviews (intensive) + Re-Jirah | timed, cold + spaced revision | P0 | 12 | To Do
6-55 | Sprint 6 | Career | Applications + take-homes (ongoing) | deep-dives, assignments | P0 | 8 | To Do

## Sprint Plan
Sprint | Dates (2 wks, Sun off) | Theme | Key Deliverable / Demo at sprint-end | Apply?
Sprint 1 | 22 Jun – 04 Jul | Foundations + Setup | 5 foundation concepts locked; Prompt-Eng course done; first Claude API call; FinOps repo + Supabase live. | Not yet
Sprint 2 | 06 Jul – 18 Jul | M1 Extraction Core (Python) | Upload invoice -> structured JSON via FastAPI/Pydantic (Postman). TDS math in deterministic code. | Not yet
Sprint 3 | 20 Jul – 01 Aug | M1 Trust + Eval Engine | Eval Dashboard: '94% precision on 30 invoices' + tracing + version compare. ← hireable proof. | Not yet
Sprint 4 | 03 Aug – 15 Aug | M1 Full-Stack + SHIP | M1 LIVE on Vercel: slick UI, streaming, human-in-loop, eval-backed. Resume + Loom video out. | 🚩 START
Sprint 5 | 17 Aug – 29 Aug | RAG + M2 Bank Recon | RAG over past invoices; M2 reconciliation working; Dockerised local. Interviewing in parallel. | Ongoing
Sprint 6 | 31 Aug – 12 Sep | Agents + Interview Hardening | Agent feature live; full Bucket-1/3/4 coverage; mock-interview ready across all concepts. | Ongoing

## Dashboard
LIVE PROGRESS DASHBOARD
Auto-calculated from Sprint Board. Updates as Nidhi changes Status.
OVERALL (Phase 1)
Total tasks | 55
Done | 0
In Progress | 0
Blocked | 0
% Complete | 0%
Total est hrs | 438
Hrs done | 0
BY SPRINT
Sprint | Tasks | Done | % Complete | Progress | Est Hrs | Hrs Done
Sprint 1 | 9 | 0 | 0% | .................... | 70 | 0
Sprint 2 | 10 | 0 | 0% | .................... | 84 | 0
Sprint 3 | 9 | 0 | 0% | .................... | 72 | 0
Sprint 4 | 9 | 0 | 0% | .................... | 68 | 0
Sprint 5 | 9 | 0 | 0% | .................... | 72 | 0
Sprint 6 | 9 | 0 | 0% | .................... | 72 | 0
TOTAL | 55 | 0 | 0% |  | 438 | 0

## Phase 2 Backlog
PHASE 2 — BETTER COMPANIES / GROWTH (after job, or in parallel — no fixed dates)
Item | Sub-topics | Priority | Est Time | Status
Build: M3 Procurement | optimization, constraint-satisfaction, LP solver, multi-objective scoring, what-if | P2 | 1–2 wk | To Do
Graph RAG | NetworkX, vendor-fraud-network detection | P2 | 3–4 d | To Do
LlamaIndex | framework RAG vs from-scratch | P2 | 3 d | To Do
Multi-agent + MCP server | agent collaboration, build MCP tools | P2 | 1 wk | To Do
Agent memory | episodic / semantic / procedural | P2 | 2–3 d | To Do
Cloud / MLOps (deep) | Docker deep, Kubernetes, AWS/GCP — gates highest pay | P2 | 4–6 wk | To Do
LangChain + LangSmith / Phoenix | orchestration + agent tracing / token-cost | P2 | 1 wk | To Do
Fine-tuning / LoRA-QLoRA | when vs prompt, PEFT, data prep | P2 | 1 wk | To Do
Quantization + Ollama | local LLMs, 4/8-bit | P2 | 1 wk | To Do
System design (deep) | LLM-app architecture, scale, failure | P2 | 1 wk | To Do
TypeScript migration | if not done in Phase 1 | P2 | 3–4 d | To Do
Cert: CCA-F | Claude Certified Architect Foundations | P2 | ~1 wk | To Do
Cert: DeepLearning.AI GenAI w/ LLMs | Andrew Ng, weekends | P2 | 3–4 wk | To Do
Discuss-fluently set | distillation, MoE, Constitutional AI, RLHF vs DPO | P2 | 3–4 d | To Do